## Sheet1
[5 empty] | Product Increment 1 |  |  | Product Increment 2 |  |  | Product Increment 3 |  |  | Product Increment 4
Features | User Stories | T-shirt size | Storypoints | Order/ Priority | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21
[5 empty] | #REF! | #REF! | #REF! | 40 | #REF! | #REF! | #REF! | #REF! | #REF! | 60 | #REF! | 61 | 37
Global Components | Header | L | #REF! |  | y
Global Components | Footer | M | #REF! |  | y
Global Components | Mega Menu | L | #REF! |  | y
Global Components | Alert Bar | L | #REF! |  | y
Global Components | Alert Bar for mobile | S | 2 |  |  |  |  | y
Global Components | Mega Menu for mobile | M | 3 |  |  |  |  | y
Homepage | Hero-Image | M | #REF! |  | y
Homepage | Hero - Global Search | L | #REF! |  |  | y
Homepage | Hero- Regional Search | L | #REF! |  |  | y
Homepage | Featured Tiles | L | #REF! |  | y
Homepage | Global Search | L | 5 |  | y
Homepage | News Tile- Large and Small | L | 5 |  |  | y
Homepage | Region Locator | M | 3 |  |  | y
Homepage | Featured Set - Home Popular Services | L | 5 |  |  | y
Homepage | Featured Set - Home Popular Programs | L | 5 |  |  |  | y
Homepage | Featured Banner | M | 3 |  |  | y
Homepage | Social Tiles | L | 5 | [6 empty] | y
Search Functionality - Auto Complete |  | L | 5 |  |  | y
Cognitive Search Functionality
Navigation Landing | Hero - Text Only | M | 3 |  |  | y
Navigation Landing | Topics Menu | L | 5 | [5 empty] | y
Navigation Landing | Search Box | M | 3 | [5 empty] | y
Navigation Landing | Navigation landing taxonomy | L | 5 |  |  |  | y
Topic Landing | Hero - Text Only | XS | 1 |  |  |  | y
Topic Landing | Programs Menu | L | #REF! |  |  |  | y
Topic Landing | Resources Menu | L | #REF! |  |  |  | y
Topic Landing | Related Links Card | M | 3 |  |  |  | y
Program | Hero - Image | L | #REF! | [5 empty] | y
Program | Content Block - Text | M | #REF! |  |  |  | y
Program | Side Navigation | L | 5 |  |  |  |  | y
Program | What We Do Icons | M | 3 |  |  |  |  | y
Program | Featured Cards - Text | M | 3 |  |  |  |  | y
Program | Featured Cards - Image | L | 5 |  |  |  |  | y
Program | Service Locator | M | 3 |  |  |  |  | y
Program | Related Links | S | 2 |  |  |  |  | y
Program | Icon Categories | M | 3 |  |  |  |  | y
Program | Program Specific Banner | M | 3 | [5 empty] | y
Program | Contact Card - Vertical | M | 3 |  |  |  |  | y
Program | Contact Card - Accordian | L | 5 |  |  |  |  | y
Program | Contact Card - Horizontal | M | 3 |  |  |  |  | y
Child | Content Block - Text | XS | #REF! | [7 empty] | y
Child | Accordion - FAQ's | M | 3 | [5 empty] | y
Child | Accordion - Contact Card | XS | 1 | [7 empty] | y
Child | Contact Form | L | 5 | [5 empty] | y
Child | Content Block - Data | M | 3 | [5 empty] | y
Child | Content Block - Graph | L | 5 | [5 empty] | y
Search | Hero - Text Only | XS | 1 | [7 empty] | y
Search | Search Bar | L | #REF! | [6 empty] | y
Search | Filter Bricks | M | #REF! | [6 empty] | y
Search | Filters Panel | L | #REF! | [6 empty] | y
Search | Search Results | M | #REF! | [6 empty] | y
Search | Pagination | S | #REF! | [6 empty] | y
News Directory | Hero - Text Only | XS | 1 | [7 empty] | y
News Directory | Filters Panel | M | 3 | [5 empty] | y
News Directory | Post Card | M | 3 | [7 empty] | y
News Directory | Pagination | S | 2 | [7 empty] | y
News Directory | Contact Card - Vertical | XS | 1 | [6 empty] | y
Regional search | Regional search | L | #REF! | [6 empty] | y
Region | Nearby offices component | XL | 10 | [7 empty] | y
Region | Hero - Image | XS | 1 | [6 empty] | y
Region | Side Navigation | M | 3 | [7 empty] | y
Region | Featured Cards - Text | M | 3 | [7 empty] | y
Region | Related Links | XS | 1 | [9 empty] | y
Region | Contact Card - Accordian | S | #REF! | [7 empty] | y
Region | Contact Card - Vertical | S | 2 | [7 empty] | y
Program Directory | Hero - Text Only | XS | 1 | [6 empty] | y
Program Directory | Search Bar | M | 3 | [7 empty] | y
Program Directory | Search Results - Program | L | 5 | [7 empty] | y
Program Directory | Filters Panel | M | 3 | [7 empty] | y
Program Directory | Pagination | S | 2 | [8 empty] | y
Contact | Hero - Text Only | XS | 1 | [8 empty] | y
Contact | Contact Card - Horizontal | M | 3 | [8 empty] | y
Contact | Region Locator | M | 3 | [8 empty] | y
Contact | Content Card - Multiple | M | 3 | [9 empty] | y
Contact | Help Form | L | 10 | [9 empty] | y
News Release | Content Block | XS | 1 | [9 empty] | y
News Release | Image - Horizontal | S | 2 | [8 empty] | y
News Release | News Release - Image | M | 3 | [9 empty] | y
News Release | Newsletter Box | M | #REF! | [9 empty] | y
Intranet - Taxonomy |  | L | #REF! | [9 empty] | y
Intranet Home Page Templates | Personalized Tiles- Pulling from Sharepoint | L | 5 | [9 empty] | y
Intranet Home Page Templates | Social Tiles | M | 5 | [8 empty] | y
Intranet Home Page Templates | Personalized Tiles- Pulling from New Employee Resources | M | 3 | [8 empty] | y
Intranet Home Page Templates | Event Search | M | 3 | [8 empty] | y
Intranet Home Page Templates | Survey/Poll Tile | M | 3 | [8 empty] | y
Intranet Home Page Templates | News Tile Large and Small | M | 3 | [8 empty] | y
Intranet Home Page Templates | Personalized Tiles- My Quick Links | XL | 10 | [8 empty] | y
Intranet Home Page Templates | Tool Tip | S | 2 | [8 empty] | y
Intranet Home Page Templates | Moodle Integration | XL | 10 | [7 empty] | y
Intranet Home Page Templates | Personalized Tiles- My Trainings | L | 5 | [8 empty] | y
Intranet Home Page Templates | What's happening today widget | M | 3
Intranet Home Page Templates | Extra large news tile | S | 2 | [8 empty] | y
Intranet Home Page Templates | Footer | S | 2 | [8 empty] | y
Intranet Home Page Templates | Header | S | 2 | [8 empty] | y
Intranet Landing Page Templates | Hero - Image | XS | 1
Intranet Landing Page Templates | Content Block - Text | S | 2
Intranet Landing Page Templates | Featured Cards - Image | M | 2 | [9 empty] | y
Intranet Child Page Templates | Related Forms | XS | 1
Intranet Child Page Templates | Related Policies | M | 3
Intranet Child Page Templates | Search Results - Program | M | 3
Intranet Child Page Templates | Filters Panel | M | #REF!
Intranet Child Page Templates | Pagination | S | 2 | [9 empty] | y
Other similar internet components |  | XL | #REF! | [8 empty] | y
365 SSO |  | L | #REF! | [5 empty] | y
Office 365 integrations - Outlook and SharePoint |  | XL | #REF! | [6 empty] | y
Pre-UAT training |  | XXL | #REF! | [9 empty] | y
Multi-lingual configuration |  | XL | #REF! | [7 empty] | y
Adminstration - Custom workflows and roles |  | XL | #REF!
WebForm | Webform configuration and customization | L | 5
Content migration | Planning | XL | 10 | [9 empty] | y
Content migration | Build | XL | 10
Content migration | Execute- Automated | XXL | 20 | [10 empty] | y
Content migration | Execute - Manual | XXL | 20 | [10 empty] | y
Content migration | Manual Web form migration | XL | 10 | [11 empty] | y
Content migration | Test | L | 5 | [11 empty] | y
Content migration | Deploy | XXL | 20 | [12 empty] | y
Content migration | Reconciliation | XL | #REF! | [11 empty] | y
Content migration | Table migration QA | XL | 10 | [11 empty] | y
Intranet Gallery Page Templates | Intranet Gallery Page Templates | XL | 10 | [9 empty] | y
Intranet Event Page Templates 1 |  | XL | 10 | [10 empty] | y
Intranet Events page Template 2 |  | L | #REF! | [9 empty] | y
Phonebook page |  | XL | 10 | [10 empty] | y
SEO | BreadcrumbList schema is included on pages where breadcrumbs are present | M | 3 | [11 empty] | y
SEO | Government Organization schema is included on the homepage | M | 3 | [11 empty] | y
SEO | Sitelinks Searchbox schema in included on the homepage | M | 3 | [11 empty] | y
SEO | FAQ schemas included on pages with FAQ content | M | 3 | [11 empty] | y
SEO | H1, H2, and further header tags exist and are wrapped around relevant page titles | S | 2 | [11 empty] | y
SEO | Current-state excess H1 tags should be stripped on redesigned pages, so that each page has one and only one H1 tag | M | 3 | [11 empty] | y
SEO | All content is included as HTML text | M | 3 | [11 empty] | y
SEO | Page loads via SSR or pre-rendering | M | 3 | [11 empty] | y
SEO | All meta-description fields are populated with optimized meta-data | M | 3 | [11 empty] | y
SEO | Page title field exists | xs | 1 | [12 empty] | y
SEO | Optimized page titles are included on every page | s | 2 | [12 empty] | y
SEO | Meta-keywords field should not be populated | s | 2 | [12 empty] | y
SEO | Canonical is included on every page | M | 3 | [12 empty] | y
SEO | Canonical is overridable by the Business Manager | S | 2 | [12 empty] | y
SEO | Alt text fields exist for all images | xs | 1 | [12 empty] | y
SEO | Alt text is included for all images | xs | 1 | [12 empty] | y
SEO | URL structure follows SEO best practice | M | 3
SEO | XML sitemap should exist for DSHS site | M | 3 | [12 empty] | y
SEO | XML sitemap formatting should follow best practice | S | 2 | [12 empty] | y
SEO | A robots.txt file should exist on site | M | 3 | [12 empty] | y
SEO | XML sitemap should be linked to from the DSHS robots.txt file | M | 3 | [12 empty] | y
SEO | Valid Pagination variants should have self-referential canonicals | M | 3 | [12 empty] | y
SEO | Image Compression | S | 2 | [12 empty] | y
SEO | Lazy Loading | M | 3 | [12 empty] | y
SEO | Define browser caching policy | M | 3 | [12 empty] | y
SEO | Javascript Optimization | M | 3 | [12 empty] | y
SEO | Custom 404 | S | 2 | [12 empty] | y
SEO | Redirect Mapping | M | 3 | [13 empty] | y
SEO | Redirect mapping logic rules | S | 2 | [12 empty] | y
SEO | Block internal search URLs to Google | M | 3 | [13 empty] | y
SEO | Update internal links | S | 2
SEO | Block staging site from search engine crawlers | S | 2 | [13 empty] | y
SEO | HTML links should exist between English and Spanish content variants | S | 2 | [13 empty] | y
SEO | English and Spanish-language content variants should live at their own unique URLs | M | 3 | [13 empty] | y
SEO | If Spanish translation of page does not exist, then link to the English page version | M | 3 | [13 empty] | y
SEO | Breadcrumb hierarchy should match page navigation | M | 3 | [13 empty] | y
SEO | Pages should contain hreflang | M | 3 | [13 empty] | y
Configuration | Export Codebase, Files and DB to DSHS Acquia instance | M | 3 |  |  |  | y
Configuration | Setup GitHub code repo and continous integration | L | 5 |  |  |  | y
Configuration | Controlling access to Cloud Platform | S | 2 |  |  |  | y
Configuration | SSO and Outlook Integration test | L | 5 |  |  |  | Y
Configuration | DNS Configuration | L | 5 | [13 empty] | y
Configuration | Admin accounts setup Intranet | L | 5 | [13 empty] | y
Configuration | Admin accounts setup Public site | L | 5 | [13 empty] | y